## rmsa
INSPECTION REPORT ON STAUS OF 100% COMPLETED SCHOOLS UNDER RMSA PHASE - I / II
Name of the District:
1 | Name of the Mandal: | [7 empty] | 2 | Nameof the Village:
3 | Name of the school with location: | [7 empty] | 4 | School Code: (UDISE CODE)
5 | Type of construction: |  | G / G+1 / G+2 | [5 empty] | 6 | Tender Discount:
7 | Agreement Contract value | [7 empty] | 8 | Thirdy Party Quality Control reports available ?
9 | Date of Agreement: | [7 empty] | 10 | Date of Handing over Building :
11 | Building taken over in the prescribed proforma of Handing over checklist | [7 empty] | 12 | Statuatory Recoveries are effected as per agreement and remitted to respective Depts.
13 | Components Sanctioned and Physical Work Progress |  |  |  | (Answer with Yes /No as per ground reality)
| Name of the componenet | Amount Approved Rs. in lakhs | Status of 100 % completed components
|  |  | Roof | Flooring | Doors | Windows | Plastering | Painting | Distempering | Electrification | Toilets and Water supply | Parapet wall | Finishing (as per specifications) | Fit for occupation (Soundness Certificate ) | Remarks
| Additional Class Room (2) (tx7m) | 9.26
| Laboratory (7mx7m) | 4.6
| Computer Room (7mx7m) | 4.6
| Art/craft Room (7mx7m) | 4.6
| Library (10mx7m) | 6.75
| Toilet Blocks | 1
| Drinking Water Facility | 0.5
14 | Total Amount Received from the Head Quarters Installment wise with Date | [6 empty] | 15 | Bank Account Number with Name of the bank and IFSC code
| Installment | Date of receipt | Amount Received | Date of Payment | Payment Made bySMDC |  | Interest gained on civil amounts |  | A/C Number:
[5 empty] | contractor | Engineer |  |  | IFSC CODE:
Name of the Branch:
[8 empty] | 16 | Mobile Number of the HM:
[8 empty] | 17 | Tender Document Available in School (yes/no)
[8 empty] | 18 | Agreement copy with Contractor Avaible in School (Yes/No)
| Total Amount Received | [6 empty] | 19 | Photes enclosed |  | (yes/No)
20 | Balance Amount Available of the civil works with SMDC | Civil works Amount | Interest | Total
21 | Openion of the Headmaster | [6 empty] | 22 | Openion of the Observer